## Slide 1: Behavioral Health Carve-in Meeting with External Stakeholder Advisory Board November 20, 2020

## Slide 2: Agenda
Background, Mission and Goals
1
Project Phases and Timing
2
Phase I Updates
3
Upcoming Next Steps
4

## Slide 3: Background, Mission and Goals Jessie Dresner

## Slide 4: Background
The Missouri HealthNet Division (MHD) and its sister agencies (State) are working to carve select behavioral health (BH) services into managed care (MC).
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 25 | 25 | 25 | 25
BH
Carve-In
MHD
Children’s
Division (CD)
Division of Behavioral Health (DBH)

## Slide 5: Background
The State’s BH carve-in initiative covers the following populations (herein referred to as Category of Aid 4 or COA 4):
Children in the care and custody of the State through CD or DYS and children in the juvenile court system
Children who receive adoption subsidy assistance
Roughly 19,000 children
Roughly 23,000 children

## Slide 6: Background
COA 4 children are often involved in multiple child-serving systems and they need a tightly coordinated approach to obtain desired outcomes for children and families
This can be challenging without an integrated payment and service delivery system
A Medicaid MC environment provides opportunities not present in a FFS environment
Enhanced care coordination, access to a coordinated network of providers, and provision of whole person care
To realize these benefits, MHD will move some BH FFS benefits into MC and procure a specialty vendor to administer physical health (PH) and BH benefits to COA 4 kids
COA 4 children currently receive most of their Medicaid PH services through MC and their BH services through fee-for-service (FFS)
These children have greater level of care needs than non-custodial children

## Slide 7
State’s Mission Statement for COA 4 BH Carve-In
To establish a trauma-informed, comprehensive and integrated BH/PH delivery system that allows children and youth, both those in the care and custody of the state and those receiving adoption subsidy assistance, to grow into healthy adults and live full and satisfying lives.

## Slide 8: Initiative Goals
Enhance cross-system partnerships and trauma informed care2 across child-serving systems to strengthen coordination and improve the well-being of children, youth and families.
2
Promote early identification, prevention and treatment to support resiliency and recovery for children, youth and families.
Leverage specialty vendor’s resources, in partnership with providers, to support whole person care and provide care coordination.
Establish a comprehensive PH and BH provider network that specializes in the targeted population.
Establish an effective partnership amongst all stakeholders to build a quality strategy emphasizing accountability, BH/PH integration and health outcomes and drive the system towards value-based care.
2 For more information, please refer to https://dmh.mo.gov/trauma and https://dmh.mo.gov/media/pdf/missouri-model-developmental-framework-trauma-informed-approaches

## Slide 9: Carve-in Framework
Funding Sources
Current Missouri BH Service Offerings
Today’s Delivery Model for COA 4 Kids
Administering Agency
COA 4 Delivery Model Post Carve-In
New BH Services Under Carve-In
Residential Services and Family First Prevention Services Act (FFPSA)

## Slide 10: Project Phases and Timing Bobbi Jo Garber

## Slide 11: Project Phases and Timing
Phase I: Planning and Design
4-6 Months
Research, Vision, Design, Internal Stakeholder Engagement, External Stakeholder Strategy
Phase II: Execution
9-12 months
HP Responsibilities, RFP and Rate Development, Procurement , Stakeholder Engagement and CMS Engagement
Phase III: Implementation
9-12 months
Readiness, Technical Assistance, IT System Modifications, Federal Authorities, State Regulations, State Oversight
Phase IV: Monitoring
3-6 months
Ongoing monitoring and oversight

## Slide 12: Project Phases and Timing
State Regulations and Licensure
New regulations needed for PRTFs and QRTPs
Time needed to review applications and grant licensure to providers
HP Network Development and Provider Technical Assistance
Sufficient time needed to ensure a smooth transition for COA 4 members and enable overall system stability
Family First Protection Services Act (FFPSA)
Work related to FFPSA directly impacts timing of decisions, funding, and implementation of residential services (CD residential facilities, QRTPs and PRTFs)
State is currently working toward a July 1, 2022 implementation date
Key considerations for this timeline include:
Competitive HP Procurement
Requires roughly 12 months to draft RFP, review responses and make award
Federal Authorities and CMS Approval
New authorities and authority amendments needed (e.g., State Plan amendment)
CMS approval of rates and HP contracts also needed

## Slide 13: Phase I: Planning and Design
May 2020 through September 2020
Developed a mission and goals to guide the initiative
Established internal stakeholders, roles and responsibilities
Identified and established key decision points needed for carve-in
  BH services that will be carved into MC
  Multiple HPs versus single, specialty HP
  Enrollment and eligibility issues
  Procurement process

## Slide 14: Phase I: Planning and Design
May 2020 through September 2020
Designed strategy for external stakeholder engagement
  Appointed External Stakeholder Advisory Board
  Developing COA 4 BH Carve-in dedicated webpage
Reviewed federal and state authorities impacted by BH carve-in
  State Regulations and Statutes
  State Plan and Waivers
Researched national trends for Medicaid MC Care for the Foster Care population
  Manage Care integrated Care

## Slide 15: Phase II: Execution
October 2020 through September 2021
Conduct stakeholder engagement activities
Identify the roles and responsibilities of the HP to inform RFP
  Modify any necessary elements of MHD’s existing HP contract
  Draft language for new HP contract provisions specific to carve-in
    Anticipated new sections include:
      care management
      network benefits
      quality

## Slide 16: Phase II: Execution
October 2020 through September 2021
Develop and issue COA 4 MC Request for Proposal (RFP)
Review RFP responses and award to selected HP
Engage CMS on modifications needed to Federal Authorities (State Plan and waivers)

## Slide 17: Phase III: Implementation
July 2021 through June 2022
Continue stakeholder engagement activities
Conduct readiness assessments on selected HP
  Desk and on-site reviews
Deliver technical assistance to providers
Deliver technical assistance to selected HP
Provide education to beneficiaries and caregivers
Establish State monitoring and oversight roles of MC Program
Launch COA 4 single HP model on 7/1/2022

## Slide 18: Phase IV: Monitoring
July 2022 through December 2022
Conduct monitoring and oversight on COA 4 MC program
Monitor and address issues that arise
Assess member satisfaction

## Slide 19: Phase I Updates Eric Martin

## Slide 20: Phase I Updates
Phase I Key Decisions
State will contract will be a single, specialty HP that administers Medicaid PH and select BH benefits to the COA 4 population
MHD will procure the single, specialty HP through an open, competitive procurement
COA 4 children will be mandatorily enrolled into specialty HP

## Slide 21: Phase I Updates
Services Currently in MC for COA 4 Children
Inpatient Hospital PH Emergency Room Emergency Transportation Outpatient Hospital PH Clinics (FQHCs) Physician Laboratory/X-ray Optometric Dental Family Planning DME Non-emergent medical transportation

## Slide 22: Phase I Updates
BH Services that will be Carved into MC on July 1, 2022 | New Service with Potential State Plan Changes | HP Administering Agency | Oversight Agency
Inpatient BH Includes State-operated psychiatric residential treatment facilities (PRTFs) |  | MHD | DBH/DHSS
Outpatient BH Clinics (including CMHCs/CCBHOs)1 Physician Other licensed practitioners Medically necessary counseling services discovered through EPSDT screening |  | MHD | MHD/DBH
Qualified Residential Treatment Program Services (QRTP)3 | X | MHD | CD
Non-State Operated PRTFs4 | X | MHD | MHD/CD/DHSS
1 Does not include CPR or CSTAR services
2 CD is working toward FFPSA compliance by October 1, 2021.
3 Does not include Room and Board Per Diems
4 CD has licensing authority for CD licensed residential treatment and
QRTP through MOU between DSS and DHSS.

## Slide 23: Phase I Updates
New in lieu of Service Options Effective July 1, 2022
Intensive Outpatient (IOP)
Partial Hospital (PHP)

## Slide 24: Phase I Updates
BH services that will continue to be covered outside of managed care | Administering Agency
DBH Community Psychiatric Rehabilitation (CPR) | DBH
Comprehensive Substance Treatment and Rehabilitation Services (CSTAR) | DBH
CCBHO CPR/CSTAR Services | DBH
Targeted Case Management Services | DMH
DYS Rehabilitative BH Services | DYS
Applied Behavioral Analysis for ASD | MHD

## Slide 25: Upcoming Next Steps Amber McKenzie

## Slide 26: Upcoming Next Steps
Task | Timeline
State to draft RFP Review best practices in other COA 4 single HP models Define HP role and responsibilities Craft RFP language and MC provisions | September 2020 – December 2020
State to perform internal RFP reviews and approvals | January – June 2021
Mercer to develop COA 4 capitation rates | October 2020 – May 2021
State to release RFP | July 2021
Vendors respond to RFP | August 2021
State to review responses, select vendor and issue award | September 2021
Key Procurement Tasks and Timelines

## Slide 27: Upcoming Next Steps
Anticipated Additional Meetings with Stakeholder Advisory Board
December 2020
February 2021
April 2021
June 2021

## Slide 28: Open Discussion

## Slide 29: Contact Information
Email us your questions, comments or feedback to MHD.BHCARVEIN@dss.mo.gov

## Slide 30: Stakeholder Input on Contract Sections
Domain | Contract Page # | Contract Section | Section Reference
General Requirements | 16 | Local Community Care Coordination Program (LCCCP) | 2.1.7.c
General Requirements | 33 | Prior Authorization | 2.5.5
General Requirements | 35 | Certification Review | 2.5.6
General Requirements | 37 | Transition of Care | 2.5.9
General Requirements | 67 | Care Management and Disease Management | 2.11
General Requirements | 115 | Provider Services Staff | 2.16.1
General Requirements | 116 | Website for Providers | 2.16.3
General Requirements | 123 | Quality Assessment & Improvement: Practice Guidelines | 2.18.5